## Slide 1
14 SEPTEMBER 2023| Online
Anne Furphy
Project Manager at Chamber of Commerce of Seville
Anne.furphy@camaradesevilla.com
4th online meeting
“PIT”

## Slide 2
OUR AGENDA
Relevant information
Communication
Learning Phase
Meeting in Croatia
TOTAL

## Slide 3
RELEVANT INFORMATION
12.3 MEUR
FROM INTERREG EUROPE:
Portal is opened for reporting: But for the moment we have to wait until RfC of Greek partners is officially accepted.
26 to 28 September 2023 (Lille/France): Lead Partner workshop on reporting activities, finances and communication. Both LP and Lapland U. attend.
This event is targeted at lead partners, lead partners’ financial managers and controllers as well as communication managers.

## Slide 4
12.3 MEUR
REMEMBER THE DEDICATED LINK TO HELP ON PROJECT IMPLEMENTATION IN INTERREG EUROPE WEBSITE:
https://www.interregeurope.eu/help/project-implementation-2021-2027
10 points to remember for the kick-off phase

## Slide 5
COMMUNICATION
OUR WEBSITE IS VERY LIVELY!
PUBLISH EVENT IN CROATIA IN WEBSITE
PUSH SOCIAL MEDIA ANIMATION (PP2) with partners
COMMUNICATE AND INVOLVE STAKEHOLDERS
SCRIPT FOR OUR 1ST VIDEO

## Slide 6
-Check 1st stakeholders group meetings organized until now:
LP: 15/09
PP2: 29/09
PP3:
PP4: OK x2
PP5:
PP6: OK
PP7: OK
PP8:
REPORT YOUR MEETING WITH STAKEHOLDERS AND SHARE IT WITH REST OF PARTNERS
https://drive.google.com/drive/folders/1wnbMy5RlQTzYKWR1JF75PS51zOxfTna4?usp=share_link
STAKEHOLDERS’ GROUP

## Slide 7
FIND THE TEMPLATE HERE:
https://docs.google.com/document/d/1fQqHMA67B17Vrl7bYJP8dI7z-IlFXv1h/edit?rtpof=true
SoA- INITIAL ASSESSMENT
LEARNING PHASE
IDENTIFICATION OF GOOD PRACTICES
SUPPORTING DOCUMENTS:
https://docs.google.com/document/d/1ctg4GB55c70PQFiO7tZYOWu6Q23v5Rhh/edit?usp=sharing&ouid=115705946630176294194&rtpof=true&sd=true
https://drive.google.com/drive/folders/1riiIedSiYpVpQAhF49HLmO5xhmH3qfyQ?usp=sharing
LET’S START!

## Slide 8
PRELIMINARY AGENDA
CROATIA EVENT

## Slide 9
COMPLETE SoA ASSESSMENT
MEET STAKEHOLDERS
IDENTIFY BEST PRACTICES
FILL IN PRELIMINARY QUESTIONNAIRE TO BE SENT IN THE NEXT DAYS
PREPARE OUR EVENT IN CROATIA:
  INVITE STAKEHOLDERS TO JOIN THE EVENT
  FILL IN THE PARTICIPANT LIST
GET READY FOR 1st PROGRESS REPORT AND FOR THE USE OF THE PORTAL
TO-DO’s in the next weeks

## Slide 10
Time for questions
?

## Slide 11
Thank you!
www.interregeurope.eu/TOURBO