## Slide 1
22 JANUARY 2024| Online
Anne Furphy
Project Manager at Chamber of Commerce of Seville
Anne.furphy@camaradesevilla.com
7th online meeting
“PIT”

## Slide 2
OUR AGENDA
Reporting
Learning Phase
What is next
TOTAL

## Slide 3
REPORTING
12.3 MEUR
PARTNER | FINANCIAL REPORT | POLICY REPORT | COMMENTS
CCSEV | READY | READY | 
LAPLAND | Submitted | READY | + missing communication report input
VRATSA | READY | READY | 
MARCHE R. | Submitted | READY | 
BREMERH. | Submitted | To be completed | Some pending amendments needed for the policy instrument report.
PORA | READY | READY | 
DONEGAL | Not submitted | READY | 
ELORIS | Submitted | Not ready | + missing pilot action input
GENERAL COMMENTS:
Please be more specific in Policy report,
Indicate date of stakeholders meetings,
Detail stakeholders involved,
Detail activities conducted at internal level and
How you involve your policy authority (if procedes)
SUBMISSION DATE 1ST FEBRUARY 2024

## Slide 4
DONE:
PORA
DONEGAL
BREMERHAVEN (to be reduced)
MARCHE REGION
MISSING: THE REST!!
SoA- INITIAL ASSESSMENT
COMPLETE GGPPs TEMPLATES
DONE:
6. "Internal areas strategy" and Tu.Ris.Marche
UNDER REVIEW:
Lapland University (FI)
1. Sustainable Travel Finland (STF)
2. VÄLKKY
3. VALUE (Growth & Value through Sustainability Communication)
Experience Bremerhaven (DE)
4. Digital pilot for Bremerhaven SMEs
Seville C.C (ES)
5. Andalucía Lab
Donegal County Council (IE)
7. Green for Business

## Slide 5
EVENT IN FINLAND
BOOK THE DATES
8-12 APRIL 2024 (working days 9-10-11 (until 14,00))
CHECK TRAVELLING OPTIONS
INFORM STAKEHOLDERS
TO-DO
AGENDA (LAPLAND+CCSEV review)
Day1
Format of Exchange and workshops
Special guest
Study visits
Day2
Format of Exchange and workshops
Special guest
Study visits
Day3
Steering Committee meeting
In paralell (possibility of final study visit)
INVITE FORMALLY STAKEHOLDERS (All partners)
PRACTICAL INFORMATION (LAPLAND with partners)
CREATE NEW EVENT IN WEBSITE (LAPLAND)
FOCUS ON EXCHANGE OF PRACTICES FOR SUSTAINABILITY IN TOURISM SMES

## Slide 6
WHAT IS NEXT
TO-DO at short term
STAKEHOLDERS MEETING Nº 2
(February 2024 the latest: end of 2nd semester)
Purpose:
Gather your group of stakeholders
Present practices selected for Interreg Europe platform and explain their objectives, functioning, outcomes, transferring possibilities to your territories.
Is there a practice of your stakeholders interest, is it transferrable or aplicable to your policy instrument and/or to your organization?
Share information on pilot action and imminent launch of CALL FOR KNOWLEDGE PROVIDERS.

## Slide 7
WHAT IS NEXT
PILOT ACTION – REMEMBER THE CALENDAR
From February to September 2024 - Call for Knowledge Providers (KPs) issued at EU level: expert consultants register to the TOURBO Longlist.
SOON WEB PAGE WILL BE READY FOR DOCS DOWNLOAD
FINAL VERSION OF THE KPS CALL
DISSEMINATION IS NEEDED
INTERNATIONAL TOURISM FAIR IN MILAN
September 2024 - Call for innovation projects: tourism MSMEs based in Marche Region/Eloris submit proposals in partnership with KPs registered in the TOURBO Longlist.
October 2024 – Selection of innovation projects: Marche Region/Eloris select n.5 innovation projects proposed by Tourism MSMEs and awards each of them with a voucher of 8000EUR.
Until August 2025 – Implementation of innovation projects: the n.5 tourism MSMEs selected will implement their innovation project with the support of partner KPs. The voucher awarded will finance the consultancy provided by KPs.

## Slide 8
Thank you!
www.interregeurope.eu/TOURBO